## Sheet1
# | Suggested by | Description | # People | # Hours | Est. Total Hours | Assigned to | Membership
1 | mroth, apenn, zhynes, jontec | Put together Committee - entire committee needs to meet with faculty, administrators, etc. to get feedback, faculty advisors; engage directly with students to ask about what they see as role of student government; come up with alternative proposals; solicit proposals from outside; nominations process for committee? Institute Committee? | 14 | 30 | 420 | Senate to decide which of 3 "options"; vrajesh to figure out if IFC and Panhel are in support of this Committee, and who should be on it. If yes, then proceed | Some Dorm Presidents, UAP-elect, IFC, Panhel, Some Senators, Faculty Advisor, some other students, Dormcon P-elect; alternatively, reps instead of heads; chair
2 | leonidg | Implementation Plan | 10 | 5 | 50 | Committee
3 | asingham | Ways to reduce inefficiencies in proposals | 3 | 3 | 9 | TBD
4 | mroth | Check in with IFC, Panhel | 1 | 2 | 2 | vrajesh, cc mroth
5 | rileyb | Discussion on changes to DormCon and effect; would any single person have enough time to do both? Changes to dorm governments? | 11 | 2 | 22 | dorm presidents
6 | jontec | Defining what the problems are with UA | 30 | 1 | 30 | Senate
7 | asingham | Defining what the problems are with Dormcon | 15 | 1 | 15 | DormCon
8 | jontec | Communicate to students - committee should put out the competing proposals, and provide all to students | 10 | 2 | 20 | Committee
9 | zhynes | Define structure for communication with undergrads (might be through Committee); should be soliciting feedback throughout process | 10 | 1 | 10 | Committee